## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 7 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | ACADEMIC WEEKS (FROM 25/09/2023 TO 28/04/2024)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Literature Review | 1 | 7 | 1 | 7 | 100%
Data Collection | 7 | 4 | 7 | 4 | 100%
Analysis and Modelling | 11 | 4 | 11 | 4 | 100%
System Design and Implementation | 15 | 6 | 15 | 6 | 100%
Error Analysis and System Refinement | 21 | 3 | 21 | 3 | 100%
Result Evaluation/ Final Report | 24 | 6 | 24 | 6 | 100%
Project Review | 30 | 2 | 30 | 2 | 100%